## Sheet1
Date | Activities | Duration(Days)
2019-09-15 | Requirement Gathering | 10
2019-10-10 | Collection of Data | 25
2019-10-30 | Data Preparation | 20
2019-11-19 | Training Data | 20
2019-12-19 | Evaluate Model | 30
2019-12-29 | System Design | 10
2020-01-13 | UI Design | 15
2020-03-13 | System Development | 60
2020-03-23 | Optimize model | 10
2020-04-02 | Testing | 10
ll
s
| Activities | Start Date | End Date | Duration(Days)
| Requirement Gathering | 2019-09-15 | 2019-09-30 | 15
| Design | 2019-09-30 | 2019-10-10 | 10
| Development | 2019-10-20 | 2019-11-19 | 30
| Testing | 2019-11-19 | 2019-11-29 | 10
| Implementation and Documentation | 2019-11-29 | 2019-12-29 | 30
| Design | 2019-12-29 | 2020-01-18 | 20
| Develpoment | 2020-01-18 | 2020-02-07 | 20
| Testing | 2020-02-07 | 2020-03-08 | 30
| Integration and Documentation | 2020-03-08 | 2020-03-18 | 10
| Design | 2020-03-18 | 2020-03-28 | 10
Deve
Activities | Start Date | End Date | Duration
Topic Research and selection | 2019-08-01 | 2019-08-31 | 30
Research on selected topic | 2019-09-01 | 2019-10-01 | 30
Requirement Gathering | 2019-10-02 | 2019-10-30 | 28
Analysis | 2019-11-03 | 2019-11-13 | 10
Review Analysis | 2019-11-12 | 2019-11-16 | 4
WireFrame Design | 2019-11-17 | 2019-11-21 | 4
System Design | 2019-11-18 | 2019-11-22 | 4
Iteration 1
UI Design | 2019-11-22 | 2019-11-26 | 4
Development of Web App | 2019-11-26 | 2019-12-11 | 15
Development of Mobile App | 2019-12-12 | 2020-01-11 | 30
Testing | 2020-01-10 | 2020-01-12 | 2
Iteration 2
UI Design | 2020-01-13 | 2020-01-17 | 4
Development of Web App | 2020-01-15 | 2020-01-30 | 15
Development of Mobile App | 2020-01-30 | 2020-02-25 | 26
Testing | 2020-02-25 | 2020-02-27 | 2
Iteration 3
UI Design | 2020-02-28 | 2020-03-03 | 4 |  | 43678 | 43952
Development of Web App | 2020-03-02 | 2020-03-17 | 15
Development of Mobile App | 2020-03-16 | 2020-03-31 | 15
Testing | 2020-03-29 | 2020-03-31 | 2
Documentation | 2020-04-01 | 2020-05-01 | 30
Activities | Weeks
Requirement Gathering | 4
Iteration 1 | 5
Iteration 2 | 6
Iteration 3 | 5
Documentation | 4
Activities
Activities | Start Date | End Date | Duration |  | 43678 | 43956
Topic Research and selection | 2019-08-01 | 2019-08-31 | 30
Research on selected topic | 2019-09-01 | 2019-10-31 | 60
Iteration 1
Requirement Gathering | 2019-11-01 | 2019-11-16 | 15
Analysis | 2019-11-16 | 2019-11-20 | 4
Design | 2019-11-20 | 2019-11-30 | 10
Development | 2019-12-01 | 2020-01-15 | 45
Testing | 2020-01-12 | 2020-01-16 | 4
Iteration 2
Requirement Gathering | 2020-01-17 | 2020-01-22 | 5
Analysis | 2020-01-20 | 2020-01-22 | 2
Design | 2020-01-22 | 2020-01-26 | 4
Development | 2020-01-27 | 2020-02-20 | 24
Testing | 2020-02-21 | 2020-02-24 | 3
Iteration 3
Requirement Gathering | 2020-02-25 | 2020-02-29 | 4
Analysis | 2020-02-27 | 2020-02-29 | 2
Design | 2020-03-01 | 2020-03-05 | 4
Development | 2020-03-06 | 2020-03-27 | 21
Testing | 2020-03-27 | 2020-03-31 | 4
Documentation | 2020-04-01 | 2020-05-05 | 34
Formulas:
Date = [Date, row above]+[Duration(Days)]
End Date = [Duration(Days)]+[Duration(Days)]
Duration(Days) = [End Date, row above]
0
2
4
6
8
10
12
14
Research and
Requirement
Gathering
Determine
Functionality
System Design
UI Design
Application and
Website
Development
Testing
Documentation
Week(s)
Activities
Milestones